## Review Tracker
ID | Area | Endpoint | File | Issue | Requested Update | Owner | Status | Priority | Notes
1 | Network | PUT /cloud/network | RestAPI/operation_descriptions/updateNetwork.md | 802.1X section lacks inner-method clarity | Add valid outer/inner auth combinations and enterprise auth note | Documentation | Open | High | Requested by Malti
2 | Firmware | PUT /cloud/os | RestAPI/operation_descriptions/setOs.md | Firmware methods shown as HTTPS-centric | List server-based methods: HTTPS, FTPS, SFTP, SCP | Documentation | Open | High | Align with supported transport methods
3 | Certificates | PUT /cloud/certificates | RestAPI/operation_descriptions/setUpdatecertificate.md | Certificate import methods not explicit | Add supported import methods: HTTPS, FTPS | Documentation | Open | High | Match implementation behavior
4 | Certificates | PUT /cloud/certificates/{certname} | RestAPI/operation_descriptions/setRefreshcertificate.md | Refresh flow method support unclear | Clarify refresh behavior and source-method expectations | Documentation | Open | Medium | Keep wording REST-focused
5 | User Apps | PUT /cloud/apps/install | RestAPI/operation_descriptions/setInstalluserapp.md | Install transport support not confirmed | Validate supported methods with developer and update docs | Malti + Mayur | Pending Confirmation | Medium | Follow-up required
6 | Config | PUT /cloud/cloudConfig | RestAPI/operation_descriptions/setImportcloudconfig.md | Unsupported connector examples present in review | Remove unsupported entries and keep FXR90-supported connectors | Documentation | Open | High | Review comments mention GCP/websocket mismatches